## Sheet1
Vacation
Weekend
Holiday

## Master Schedule
ENETK Projects
[336 empty] | Sept. 25 |  |  | October .25 | [30 empty] | November .25 | [29 empty] | December .25 | [30 empty] | January .26 | [30 empty] | February .26 | [27 empty] | March .26 | [30 empty] | April .26 | [29 empty] | May .26 | [30 empty] | June .26 | [29 empty] | July .26 | [30 empty] | August .26 | [30 empty] | September .26 | [29 empty] | October .26 | [29 empty] | November .26 | [29 empty] | December .26
[7 empty] | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
Crew Numbers | PF/ PM | Trucks |  |  | SITE JOBS | Week Ending | 22: 2024-07-28; 29: 2024-08-04; 5: 2024-08-11; 12: 2024-08-18; 19: 2024-08-25; 26: 2024-09-01; 2: 2024-09-08; 9: 2024-09-15; 16: 2024-09-22; 23: 2024-09-29; 30: 2024-10-06; 7: 2024-10-13; 14: 2024-10-20; 21: 2024-10-27; 28: 2024-11-03; 4: 2024-11-10; 11: 2024-11-17; 18: 2024-11-24; 25: 2024-12-01; 2: 2024-12-08; 9: 2024-12-15; 16: 2024-12-22; 23: 2024-12-29; 30: 2025-01-05; 6: 2025-01-12; 13: 2025-01-19; 20: 2025-01-26; 27: 2025-02-02; 3: 2025-02-09; 10: 2025-02-16; 17: 2025-02-23; 24: 2025-03-02; 3: 2025-03-09; 10: 2025-03-16; 17: 2025-03-23; 24: 2025-03-30; 31: 2025-04-06; 7: 2025-04-13; 14: 2025-04-20; 21: 2025-04-27; 28: 2025-05-04; 5: 2025-05-11; 12: 2025-05-18; 19: 2025-05-25; 26: 2025-06-01; 2: 2025-06-08; 9: 2025-06-15; Sept. 25 29: 2025-10-05; October .25 6: 2025-10-12; October .25 13: 2025-10-19; October .25 20: 2025-10-26; October .25 27: 2025-11-02; November .25 3: 2025-11-09; November .25 10: 2025-11-16; November .25 17: 2025-11-23; November .25 24: 2025-11-30; December .25 1: 2025-12-07; December .25 8: 2025-12-14; December .25 15: 2025-12-21; December .25 22: 2025-12-28; December .25 29: 2026-01-04; January .26 5: 2026-01-11; January .26 12: 2026-01-18; January .26 19: 2026-01-25; January .26 26: 2026-02-01; February .26 2: 2026-02-08; February .26 9: 2026-02-15; February .26 16: 2026-02-22; February .26 23: 2026-03-01; March .26 2: 2026-03-08; March .26 9: 2026-03-15; March .26 16: 2026-03-22; March .26 23: 2026-03-29; March .26 30: 2026-04-05; April .26 6: 2026-04-12; April .26 13: 2026-04-19; April .26 20: 2026-04-26; April .26 27: 2026-05-03; May .26 4: 2026-05-10; May .26 11: 2026-05-17; May .26 18: 2026-05-24; May .26 25: 2026-05-31; June .26 1: 2026-06-07; June .26 8: 2026-06-14; June .26 15: 2026-06-21; June .26 22: 2026-06-28; June .26 29: 2026-07-05; July .26 6: 2026-07-12; July .26 13: 2026-07-19; July .26 20: 2026-07-26; July .26 27: 2026-08-02; August .26 3: 2026-08-09; August .26 10: 2026-08-16; August .26 17: 2026-08-23; August .26 24: 2026-08-30; August .26 31: 2026-09-06; September .26 7: 2026-09-13; September .26 14: 2026-09-20; September .26 21: 2026-09-27; September .26 28: 2026-10-04; October .26 5: 2026-10-11; October .26 12: 2026-10-18; October .26 19: 2026-10-25; October .26 26: 2026-11-01; November .26 2: 2026-11-08; November .26 9: 2026-11-15; November .26 16: 2026-11-22; November .26 23: 2026-11-29; December .26 30: 2026-12-07; December .26 7: 2026-12-13; December .26 14: 2026-12-20; December .26 21: 2026-12-27; December .26 28: 2027-01-04
|  |  |  | Trucks |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Crew Numbers | PF/ PM | Trucks | Enetk Manpower |  | ENETK
|  |  | Kyle Merrill | 5855 | PANEL SHOP WORK / DRAFTING WORK / PREFAB / INSTRUMENTATION | bar: 2024-09-29 W to 2024-09-29 T
|  |  | Seth Peterson | 5790 | IRON WORKS DUAL / TRIPACK CONTROL PANELS |  | 2024-10-20 W: 2; 2024-10-20 T: 1; 2024-12-22 T: 2; 2024-12-22 W: 2; 2024-12-22 T: 2; 2026-03-08 M: 1; 2026-03-08 T: 1; 2026-03-08 F: 1; 2026-03-15 M: 1; 2026-03-15 T: 1; 2026-03-15 W: 1; 2026-03-15 T: 1; 2026-03-15 F: 1; 2026-03-22 M: 1; 2026-03-22 T: 1; 2026-03-22 W: 1; 2026-03-22 T: 1; 2026-03-22 F: 1; 2026-03-29 M: 1; 2026-03-29 T: 1; 2026-03-29 W: 1; 2026-03-29 T: 1; 2026-03-29 F: 1; 2026-04-05 M: 1; 2026-04-05 T: 1; 2026-04-05 W: 1; 2026-04-05 T: 1; 2026-04-05 F: 1; 2026-04-19 M: 1; 2026-04-19 T: 1; 2026-04-19 W: 1; 2026-04-19 T: 1; 2026-04-19 F: 1; 2026-04-26 M: 1; 2026-04-26 T: 1; 2026-04-26 W: 1; 2026-04-26 T: 1; 2026-04-26 F: 1; 2026-05-03 M: 1; 2026-05-03 T: 1; 2026-05-03 W: 1; 2026-05-03 T: 1; 2026-05-03 F: 1; 2026-05-10 M: 1; 2026-05-10 T: 1; 2026-05-10 W: 1; 2026-05-10 T: 1; 2026-05-10 F: 1; 2026-06-21 T: 1; 2026-06-21 W: 1
Crew #1 |  |  | Loren McCray | 5305 | KBS PANEL BUILDS |  | 2024-10-27 T: 2; 2024-10-27 W: 1; 2024-12-29 M: 2; 2024-12-29 T: 2; 2025-01-05 M: 2; 2025-01-05 T: 2; 2026-04-12 M: 2; 2026-04-12 T: 2; 2026-04-12 W: 2; 2026-04-12 T: 2; 2026-04-12 F: 2; 2026-06-28 W: 1; 2026-06-28 T: 1; 2026-06-28 F: 1; 2026-07-05 M: 1; 2026-07-05 T: 1; 2026-07-05 W: 1; 2026-07-05 T: 1; 2026-07-12 M: 1; 2026-07-12 T: 1; 2026-07-12 W: 1; 2026-07-12 T: 1; 2026-07-12 F: 1
|  |  | Rami Dori | 1210 | LLR PANEL BUILD |  | 2025-10-26 T: 1; 2025-10-26 F: 1; 2025-11-02 W: 1; 2025-11-02 T: 1; 2025-11-02 F: 2; 2025-11-09 M: 2; 2025-11-09 T: 2; 2025-11-09 W: 2; 2025-11-09 T: 2; 2026-02-22 M: 1; 2026-02-22 T: 1; 2026-02-22 W: 1; 2026-02-22 T: 1; 2026-02-22 F: 1; 2026-03-01 M: 1; 2026-03-01 T: 1; 2026-03-01 W: 1; 2026-03-01 T: 1; 2026-07-05 T: 1; 2026-07-05 W: 1; 2026-07-12 T: 1; 2026-07-12 W: 1; 2026-07-12 T: 1
|  |  | Cole Kadrmas | 4252 | bar: 2026-03-01 F
|  |  | Dustin Howe |  |  |  | 2024-09-22 T: 2; 2024-09-22 T: 2; 2024-09-22 F: 2; 2024-09-22 S: 2; 2024-09-29 M: 1; 2024-09-29 T: 1; 2024-12-08 W: 2; 2024-12-08 T: 2; 2024-12-08 F: 2; 2026-03-08 T: 1; 2026-03-08 W: 1
|  |  | Bruce Spencer | 1210 | bar: 2026-06-28 T to 2026-06-28 F; 2026-07-05 M to 2026-07-05 T; 2026-07-12 M; 2026-08-30 F; 2026-09-06 M to 2026-09-06 F; 2026-12-07 F; 2026-12-13 M to 2026-12-13 F
Kolina Shantz
Jackson King
Crew #2 |  |  | Amos Madhombiro | bar: 2025-10-05 M to 2025-10-05 T
|  |  | Bryan Holst |  |  |  | 2024-09-22 M: 3
[77 empty] | 2 | 2 | 2 | 2 | [52 empty] | 2 | 2 | [209 empty] | 1 | 1
[72 empty] | 1 | 1 | [66 empty] | 2 | 2 | [204 empty] | 1
[64 empty] | 1 | 1
PROGRAMMING / SCADA WORK | bar: 2024-09-22 W
[5 empty] | CITY OF DICKINSON IGNITION / WONDERWARE REPLACEMENT |  | 2024-12-08 T: 1; 2025-10-12 M: 4; 2025-10-12 T: 4; 2025-10-12 W: 4; 2025-10-12 T: 4; 2025-10-12 F: 4; 2025-10-19 M: 4; 2025-10-19 T: 4; 2025-10-19 W: 4; 2025-10-19 T: 4; 2025-10-19 F: 4; 2025-10-26 F: 1; 2025-11-02 M: 1; 2025-11-02 T: 1; 2025-11-02 F: 1; 2025-11-09 M: 1; 2025-11-09 T: 1; 2025-11-09 W: 1; 2025-11-09 F: 1; 2025-11-16 M: 1; 2025-11-16 T: 1; 2025-11-16 F: 1; 2026-02-22 M: 1; 2026-02-22 W: 1; 2026-02-22 F: 1; 2026-03-01 M: 1; 2026-03-01 W: 1; 2026-03-01 F: 1; 2026-03-08 T: 1; 2026-03-08 T: 1; 2026-03-15 T: 1; 2026-03-15 T: 1; 2026-03-22 T: 1; 2026-03-22 T: 1; 2026-03-22 F: 1; 2026-03-29 M: 1; 2026-03-29 W: 1; 2026-03-29 F: 1; 2026-04-05 M: 1; 2026-04-05 W: 1; 2026-04-05 F: 1; 2026-04-12 M: 1; 2026-04-12 W: 1; 2026-04-12 F: 1; 2026-04-19 M: 1; 2026-04-19 T: 1; 2026-04-19 W: 1; 2026-04-19 T: 1; 2026-04-19 F: 1; 2026-04-26 M: 1; 2026-04-26 T: 1; 2026-04-26 W: 1; 2026-04-26 T: 1; 2026-04-26 F: 1; 2026-05-03 M: 1; 2026-05-03 T: 1; 2026-05-03 W: 1; 2026-05-03 T: 1; 2026-05-03 F: 1; 2026-05-10 M: 1; 2026-05-10 T: 1; 2026-05-10 W: 1; 2026-05-10 T: 1; 2026-05-10 F: 1; 2026-06-21 M: 1; 2026-06-21 T: 1; 2026-06-21 W: 1; 2026-06-21 T: 1; 2026-06-21 F: 1; 2026-06-28 M: 1; 2026-06-28 T: 1; 2026-06-28 W: 1; 2026-06-28 T: 1; 2026-06-28 F: 1; 2026-07-05 M: 1; 2026-07-05 T: 1; 2026-07-05 W: 1; 2026-07-05 T: 1; 2026-07-12 M: 1; 2026-07-12 T: 1; 2026-07-12 W: 1; 2026-07-12 T: 1; 2026-07-12 F: 1; 2026-07-19 M: 1; 2026-07-19 T: 1; 2026-07-19 W: 1; 2026-07-19 T: 1; 2026-07-19 F: 1
PETROHUNT SCADA OPTIX WONDERWARE REPLACEMENT | bar: 2025-10-26 M to 2025-10-26 T; 2025-11-02 W to 2025-11-02 T; 2025-11-09 T; 2025-11-16 W to 2025-11-16 T; 2025-11-23 M to 2025-11-23 F; 2025-11-30 M to 2025-11-30 T; 2025-12-07 M to 2025-12-07 F; 2026-02-15 M to 2026-02-15 F; 2026-02-22 T; 2026-02-22 T; 2026-03-01 T; 2026-03-01 T; 2026-03-08 M; 2026-03-08 W; 2026-03-08 F; 2026-03-15 M; 2026-03-15 W; 2026-03-15 F; 2026-03-22 M; 2026-03-22 W; 2026-03-29 T; 2026-03-29 T; 2026-04-05 T; 2026-04-05 T; 2026-04-12 T; 2026-04-12 T; 2026-04-19 M to 2026-04-19 F; 2026-04-26 M to 2026-04-26 F; 2026-05-03 M to 2026-05-03 F; 2026-05-10 M to 2026-05-10 F; 2026-05-17 M to 2026-05-17 F; 2026-05-24 M to 2026-05-24 F; 2026-05-31 T to 2026-05-31 F; 2026-06-07 M to 2026-06-07 F; 2026-06-14 M to 2026-06-14 F; 2026-06-21 M to 2026-06-21 F; 2026-07-12 W; 2026-07-19 W; 2026-07-26 W; 2026-08-09 M to 2026-08-09 F; 2026-08-16 M to 2026-08-16 F
[337 empty] | 2 | 2 | 2 | 2 |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [79 empty] | 1 | [6 empty] | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1
[337 empty] | 1 | 1 | 1 | 1
Crew #3 |  |  |  |  | GEVO OPTIX COSS PROGRAMMING | bar: 2024-12-15 T to 2024-12-15 F; 2026-05-03 M to 2026-05-03 F; 2026-05-10 M to 2026-05-10 F; 2026-05-17 M to 2026-05-17 F; 2026-05-24 M to 2026-05-24 F; 2026-06-21 M to 2026-06-21 T
GEVO OPTIX RO PROGRAMMING | bar: 2026-06-28 M to 2026-06-28 F
[5 empty] | GEVO OPTIX UF PROGRAMMING |  | 2024-09-22 W: 2; 2024-09-22 T: 2; 2024-09-22 F: 2; 2024-12-08 M: 2; 2024-12-08 T: 2; 2024-12-08 W: 1; 2026-07-05 M: 1; 2026-07-05 T: 1; 2026-07-05 W: 1; 2026-07-05 T: 1; 2026-07-12 M: 1; 2026-07-12 T: 1; 2026-07-12 W: 1; 2026-07-12 T: 1; 2026-07-12 F: 1; 2026-07-19 M: 1; 2026-07-19 T: 1; 2026-07-19 W: 1
Crew #4 |  |  |  |  | GEVO OPTIX CENTRIFUGE PROGRAMMING |  | 2024-09-29 M: 2; 2024-09-29 T: 2; 2024-09-29 W: 2; 2024-12-08 T: 2; 2024-12-08 F: 2; 2024-12-15 M: 1; 2025-10-05 M: 1; 2025-10-05 T: 1; 2025-10-05 W: 1; 2025-10-05 T: 1; 2026-07-19 T: 1; 2026-07-19 F: 1; 2026-07-26 M: 1; 2026-07-26 T: 1; 2026-07-26 W: 1; 2026-07-26 T: 1; 2026-07-26 F: 1; 2026-08-02 M: 1; 2026-08-02 T: 1; 2026-08-02 W: 1; 2026-08-02 T: 1; 2026-08-02 F: 1; 2026-08-09 M: 1; 2026-08-09 T: 1; 2026-08-09 W: 1; 2026-08-09 T: 1; 2026-08-09 F: 1
[5 empty] | GEVO OPTIX RTO PROGRAMMING |  | 2024-09-29 T: 2; 2024-09-29 F: 2; 2024-10-06 M: 2; 2024-12-15 T: 2; 2024-12-15 W: 2; 2024-12-15 T: 2; 2024-12-15 F: 1; 2025-10-05 M: 1; 2026-08-16 M: 1; 2026-08-16 T: 1; 2026-08-16 W: 1; 2026-08-16 T: 1; 2026-08-16 F: 1; 2026-08-23 M: 1; 2026-08-23 T: 1; 2026-08-23 W: 1; 2026-08-23 T: 1; 2026-08-23 F: 1; 2026-08-30 M: 1; 2026-08-30 T: 1; 2026-08-30 W: 1; 2026-08-30 T: 1; 2026-08-30 F: 1
GEVO OPTIX FLARE PROGRAMMING | bar: 2025-10-05 T; 2026-09-06 M to 2026-09-06 F
FIELD WORK
[91 empty] | 2 | 2 | 2 | 1 | 1 | [60 empty] | 2 | 2 | 2
Crew #5 |  |  |  |  | ONEOK MIDSTREAM | bar: 2024-09-22 T; 2024-12-15 M to 2024-12-15 W; 2025-10-05 T
[5 empty] | GEVO MAINTENINANCE | [793 empty] | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2025-11-02 M to 2025-11-02 W; 2025-11-09 M to 2025-11-09 T; 2025-11-16 M to 2025-11-16 W; 2026-02-22 M; 2026-02-22 W; 2026-02-22 F; 2026-03-01 M to 2026-03-01 W; 2026-03-08 M; 2026-03-08 W; 2026-03-08 F; 2026-03-15 M; 2026-03-15 W; 2026-03-15 F; 2026-03-22 M; 2026-03-22 W; 2026-03-22 F; 2026-04-05 M to 2026-04-05 F; 2026-04-12 M to 2026-04-12 F; 2026-04-19 M to 2026-04-19 F; 2026-06-21 M; 2026-06-21 W; 2026-06-21 F; 2026-06-28 M; 2026-06-28 W; 2026-06-28 F; 2026-07-05 M; 2026-07-05 W; 2026-07-12 M; 2026-07-12 W; 2026-07-12 F; 2026-07-19 M; 2026-07-19 W; 2026-07-19 F; 2026-07-26 M; 2026-07-26 W; 2026-07-26 F; 2026-08-02 M; 2026-08-02 W; 2026-08-02 F; 2026-08-09 M; 2026-08-09 W; 2026-08-09 F; 2026-08-16 M; 2026-08-16 W; 2026-08-16 F; 2026-08-23 M; 2026-08-23 W; 2026-08-23 F; 2026-08-30 M; 2026-08-30 W; 2026-08-30 F; 2026-09-06 M; 2026-09-06 W; 2026-09-06 F; 2026-09-13 M; 2026-09-13 W; 2026-09-13 F; 2026-09-20 M; 2026-09-20 W; 2026-09-20 F; 2026-09-27 M; 2026-09-27 W; 2026-09-27 F; 2026-10-04 M; 2026-10-04 W; 2026-10-04 F; 2026-10-11 M; 2026-10-11 W; 2026-10-11 F; 2026-10-18 M; 2026-10-18 W; 2026-10-18 F; 2026-10-25 M; 2026-10-25 W; 2026-10-25 F; 2026-11-01 M; 2026-11-01 W; 2026-11-01 F; 2026-11-08 M; 2026-11-08 W; 2026-11-08 F; 2026-11-15 M; 2026-11-15 W; 2026-11-15 F; 2026-11-22 M; 2026-11-22 W; 2026-11-22 F; 2026-11-29 M; 2026-11-29 W; 2026-11-29 F; 2026-12-07 M; 2026-12-07 W; 2026-12-07 F; 2026-12-13 M; 2026-12-13 W; 2026-12-13 F; 2026-12-20 M; 2026-12-20 W; 2026-12-20 F; 2026-12-27 M; 2026-12-27 W; 2026-12-27 F; 2027-01-04 M; 2027-01-04 W; 2027-01-04 F
ADDITIONAL GARDEN CREEK C&E Kenne Station | bar: 2026-04-26 M to 2026-04-26 F; 2026-05-03 M to 2026-05-03 F; 2026-05-10 M to 2026-05-10 F; 2026-05-17 M to 2026-05-17 F; 2026-05-31 T to 2026-05-31 F; 2026-06-21 T; 2026-06-21 T; 2026-06-28 T; 2026-07-05 T; 2026-07-05 T; 2026-07-12 T; 2026-07-12 T; 2026-07-19 T; 2026-07-19 T; 2026-07-26 T; 2026-07-26 T; 2026-08-02 T; 2026-08-02 T; 2026-08-09 T; 2026-08-09 T; 2026-08-16 T; 2026-08-16 T; 2026-08-23 T; 2026-08-23 T; 2026-08-30 T; 2026-08-30 T; 2026-09-06 T; 2026-09-06 T; 2026-09-13 T; 2026-09-13 T; 2026-09-20 T; 2026-09-20 T; 2026-09-27 T; 2026-09-27 T; 2026-10-04 T; 2026-10-04 T
GARDEN CREE WRAP UP | bar: 2026-06-28 T
DAKOTA MIDSTREAM | bar: 2024-12-15 W to 2024-12-15 F
Crew #6 |  |  |  |  | COUGAR FIBER |  | 2025-11-02 T: 1; 2025-11-02 F: 1; 2025-11-09 M: 1; 2025-11-09 W: 1; 2025-11-09 T: 1; 2025-11-09 F: 1; 2025-11-16 M: 1; 2025-11-16 T: 1; 2025-11-16 F: 1; 2025-11-23 M: 1; 2025-11-23 T: 1; 2025-11-23 W: 1; 2025-11-23 F: 1; 2026-03-22 M: 1; 2026-03-22 T: 1; 2026-03-22 W: 1; 2026-03-22 T: 1; 2026-03-22 F: 1; 2026-03-29 M: 1; 2026-03-29 T: 1; 2026-03-29 W: 1; 2026-03-29 T: 1; 2026-03-29 F: 1; 2026-04-05 M: 1; 2026-04-05 T: 1; 2026-04-05 W: 1; 2026-04-05 T: 1; 2026-04-05 F: 1; 2026-04-12 M: 1; 2026-04-12 T: 1; 2026-04-12 W: 1; 2026-04-12 T: 1; 2026-04-12 F: 1; 2026-04-19 M: 1; 2026-04-19 T: 1; 2026-04-19 W: 1; 2026-04-19 T: 1; 2026-04-19 F: 1; 2026-04-26 M: 1; 2026-04-26 T: 1; 2026-04-26 W: 1; 2026-04-26 T: 1; 2026-04-26 F: 1; 2026-06-21 M: 2; 2026-06-21 T: 2; 2026-06-21 W: 2
[373 empty] | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | [5 empty] | 1 | 1
[5 empty] | CLR FIBER |  | 2026-05-03 M: 1; 2026-05-03 T: 1; 2026-05-03 W: 1; 2026-05-03 T: 1; 2026-05-03 F: 1; 2026-05-10 M: 1; 2026-05-10 T: 1; 2026-05-10 W: 1; 2026-05-10 T: 1; 2026-05-10 F: 1; 2026-05-17 M: 1; 2026-05-17 T: 1; 2026-05-17 W: 1; 2026-05-17 T: 1; 2026-05-17 F: 1; 2026-05-24 M: 1; 2026-05-24 T: 1; 2026-05-24 W: 1; 2026-05-24 T: 1; 2026-05-24 F: 1; 2026-05-31 T: 1; 2026-05-31 W: 1; 2026-05-31 T: 1; 2026-05-31 F: 1; 2026-06-21 T: 2; 2026-06-21 F: 2; 2026-06-28 M: 2; 2026-06-28 W: 2; 2026-06-28 F: 2
[5 empty] | S.O.G.C |  | 2024-09-22 W: 1; 2024-09-22 T: 1; 2024-12-15 M: 2; 2024-12-15 T: 2; 2024-12-15 W: 2; 2024-12-15 T: 2; 2024-12-15 F: 2; 2024-12-22 M: 2; 2024-12-22 T: 2; 2024-12-22 W: 2; 2024-12-22 T: 2; 2024-12-22 F: 2; 2024-12-29 M: 2; 2024-12-29 T: 2; 2025-01-05 M: 1; 2025-01-05 T: 1; 2025-01-05 T: 1; 2025-01-05 F: 1; 2025-01-12 T: 1; 2025-01-12 T: 1; 2025-01-19 M: 1
[368 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 | [79 empty] | 1 | 2 | 1 | 2 | 1
SERVICE & MAINTENANCE | bar: 2025-10-26 F; 2025-11-02 M to 2025-11-02 W; 2025-11-09 W to 2025-11-09 F; 2025-11-16 T to 2025-11-16 T; 2025-11-23 T; 2025-11-23 T; 2025-11-30 T; 2026-02-22 M; 2026-02-22 W; 2026-02-22 F; 2026-03-01 T; 2026-03-01 T; 2026-03-08 M; 2026-03-08 W; 2026-03-08 F; 2026-03-15 T; 2026-03-15 T; 2026-03-22 M; 2026-03-22 W; 2026-03-22 F; 2026-03-29 T; 2026-03-29 T; 2026-04-05 M; 2026-04-05 W; 2026-04-05 F; 2026-04-12 T; 2026-04-12 T; 2026-04-19 T; 2026-04-19 T; 2026-04-26 T; 2026-04-26 T; 2026-05-03 T; 2026-05-03 T; 2026-05-10 T; 2026-05-10 T; 2026-05-17 T; 2026-05-17 T; 2026-05-24 W; 2026-05-31 W; 2026-06-07 T; 2026-06-07 T; 2026-06-14 T; 2026-06-14 T; 2026-06-21 M to 2026-06-21 F; 2026-06-28 M to 2026-06-28 F; 2026-07-05 M to 2026-07-05 T; 2026-07-12 M to 2026-07-12 F; 2026-07-19 M to 2026-07-19 F; 2026-07-26 M to 2026-07-26 F; 2026-08-02 M to 2026-08-02 F; 2026-08-09 M to 2026-08-09 F
GEVO
[5 empty] | Turbine Project |  | 2025-11-30 M: 2; 2025-11-30 T: 2; 2025-11-30 W: 2; 2025-11-30 T: 2; 2025-11-30 F: 2; 2025-12-07 M: 2; 2025-12-07 T: 2; 2025-12-07 W: 2; 2025-12-07 T: 2; 2025-12-07 F: 2; 2025-12-14 M: 4; 2025-12-14 T: 4; 2025-12-14 W: 4; 2025-12-14 T: 4; 2025-12-14 F: 4; 2025-12-21 M: 4; 2025-12-21 T: 4; 2025-12-21 W: 4; 2025-12-21 T: 4; 2025-12-21 F: 4; 2025-12-28 M: 4; 2025-12-28 T: 4; 2025-12-28 W: 4; 2025-12-28 T: 4; 2025-12-28 F: 4; 2026-03-22 M: 1; 2026-03-22 T: 1; 2026-03-22 W: 1; 2026-03-22 T: 1; 2026-03-22 F: 1; 2026-03-29 M: 1; 2026-03-29 T: 1; 2026-03-29 W: 1; 2026-03-29 T: 1; 2026-03-29 F: 1; 2026-04-05 M: 1; 2026-04-05 T: 1; 2026-04-05 W: 1; 2026-04-05 T: 1; 2026-04-05 F: 1; 2026-04-12 M: 1; 2026-04-12 T: 1; 2026-04-12 W: 1; 2026-04-12 T: 1; 2026-04-12 F: 1; 2026-04-19 M: 1; 2026-04-19 T: 1; 2026-04-19 W: 1; 2026-04-19 T: 1; 2026-04-19 F: 1; 2026-04-26 M: 1; 2026-04-26 T: 1; 2026-04-26 W: 1; 2026-04-26 T: 1; 2026-04-26 F: 1; 2026-05-03 M: 1; 2026-05-03 T: 1; 2026-05-03 W: 1; 2026-05-03 T: 1; 2026-05-03 F: 1; 2026-06-21 W: 1; 2026-06-21 F: 1; 2026-06-28 M: 1; 2026-07-05 M: 1; 2026-07-05 W: 1; 2026-07-12 M: 1; 2026-07-12 T: 1; 2026-07-12 W: 1; 2026-07-12 T: 1
[66 empty] | 1 | [354 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | [107 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
Crew #7 | bar: 2026-06-07 W to 2026-06-07 F; 2026-06-14 M to 2026-06-14 F
[442 empty] | 6 | 6 | 6 | 6 | 6 | [93 empty] | 6 | 6 | 6 | 6 | 6
[516 empty] | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 1 |  | 1 |  | 1 |  |  | 1 |  | 1 |  | 1 | [9 empty] | 1 | 1 |  | 1
[372 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [100 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
[358 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
CHORD
Loren McCray Direct Report Work | bar: 2025-10-26 M to 2025-10-26 F; 2025-11-02 M to 2025-11-02 F; 2025-11-09 M to 2025-11-09 F; 2025-11-16 M to 2025-11-16 F; 2025-11-23 M to 2025-11-23 F; 2025-11-30 M to 2025-11-30 F; 2025-12-07 M to 2025-12-07 F; 2025-12-14 M to 2025-12-14 F; 2025-12-21 M to 2025-12-21 F; 2025-12-28 M to 2025-12-28 F; 2026-01-04 M to 2026-01-04 F; 2026-02-15 M to 2026-02-15 F; 2026-02-22 M to 2026-02-22 F; 2026-03-01 M to 2026-03-01 F; 2026-03-08 M to 2026-03-08 F; 2026-03-15 M to 2026-03-15 F; 2026-03-22 M to 2026-03-22 F; 2026-03-29 M to 2026-03-29 F; 2026-04-05 M to 2026-04-05 F; 2026-04-12 M to 2026-04-12 F; 2026-04-19 M to 2026-04-19 F; 2026-04-26 M to 2026-04-26 F; 2026-05-03 M to 2026-05-03 F; 2026-05-10 M to 2026-05-10 F; 2026-05-17 M to 2026-05-17 F; 2026-05-24 M to 2026-05-24 F; 2026-05-31 T to 2026-05-31 F; 2026-06-07 M to 2026-06-07 F; 2026-06-14 M to 2026-06-14 F; 2026-06-21 M to 2026-06-21 F; 2026-06-28 M to 2026-06-28 F; 2026-07-05 M to 2026-07-05 T; 2026-07-12 M to 2026-07-12 F; 2026-07-19 M to 2026-07-19 F; 2026-07-26 M to 2026-07-26 F; 2026-08-02 M to 2026-08-02 F; 2026-08-09 M to 2026-08-09 F; 2026-08-16 M to 2026-08-16 F; 2026-08-23 M to 2026-08-23 F; 2026-08-30 M to 2026-08-30 F; 2026-09-06 M to 2026-09-06 F; 2026-09-13 M to 2026-09-13 F; 2026-09-20 M to 2026-09-20 F; 2026-09-27 M to 2026-09-27 F; 2026-10-04 M to 2026-10-04 F; 2026-10-11 M to 2026-10-11 F; 2026-10-18 M to 2026-10-18 F; 2026-10-25 M to 2026-10-25 F; 2026-11-01 M to 2026-11-01 F; 2026-11-08 M to 2026-11-08 F; 2026-11-15 M to 2026-11-15 F; 2026-11-22 M to 2026-11-22 F; 2026-11-29 M to 2026-11-29 F; 2026-12-07 M to 2026-12-07 F; 2026-12-13 M to 2026-12-13 F; 2026-12-20 M to 2026-12-20 F
CITY OF DICKINSON
YES
MANDAREE WATER TREATEMENT PLANT (check hours in project) | bar: 2026-06-07 M to 2026-06-07 F; 2026-06-14 M to 2026-06-14 F; 2026-08-09 M to 2026-08-09 F; 2026-08-16 M to 2026-08-16 F; 2026-08-23 M to 2026-08-23 F; 2026-08-30 M to 2026-08-30 F
SHOP WORK TO COMPLETE END OF MAY outside cameras / fix any indoor cameras | bar: 2026-05-10 M to 2026-05-10 F; 2026-05-17 M to 2026-05-17 F; 2026-06-21 T; 2026-06-28 T to 2026-06-28 T
[617 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
[5 empty] | TOTAL WORKLOAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 6 | 4 | 2 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 3 | 5 | 4 | 0 | 0 | 4 | 5 | 6 | 6 | 5 | 0 | 0 | 2 | 4 | 6 | 6 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 5 | 5 | 7 | 0 | 0 | 0 | 6 | 6 | 6 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 3 | 3 | 3 | 4 | 5 | 0 | 0 | 5 | 5 | 6 | 6 | 7 | 0 | 0 | 9 | 9 | 10 | 10 | 8 | 0 | 0 | 8 | 9 | 9 | 8 | 7 | 0 | 0 | 8 | 9 | 9 | 9 | 8 | 0 | 0 | 7 | 7 | 7 | 8 | 6 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 3 | 4 | 3 | 4 | 3 | 0 | 0 | 6 | 3 | 5 | 3 | 5 | 0 | 0 | 5 | 6 | 5 | 4 | 3 | 0 | 0 | 6 | 4 | 6 | 4 | 6 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 7 | 5 | 7 | 5 | 7 | 0 | 0 | 5 | 6 | 5 | 6 | 6 | 0 | 0 | 8 | 7 | 8 | 7 | 8 | 0 | 0 | 7 | 8 | 7 | 8 | 7 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 9 | 10 | 9 | 10 | 9 | 0 | 0 | 10 | 11 | 9 | 11 | 9 | 0 | 0 | 7 | 8 | 7 | 8 | 7 | 0 | 0 | 5 | 5 | 6 | 5 | 5 | 0 | 0 | 1 | 6 | 7 | 6 | 6 | 0 | 0 | 4 | 6 | 6 | 7 | 6 | 0 | 0 | 6 | 7 | 6 | 7 | 6 | 0 | 0 | 8 | 10 | 10 | 8 | 8 | 0 | 0 | 8 | 6 | 9 | 7 | 8 | 0 | 0 | 7 | 7 | 8 | 6 | 0 | 0 | 0 | 8 | 9 | 10 | 9 | 7 | 0 | 0 | 6 | 6 | 7 | 5 | 5 | 0 | 0 | 4 | 4 | 5 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
[5 empty] | CURRENT AUTOMATION MANPOWER | [14 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
[5 empty] | OVER / UNDER |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -5 | -4 | -3 | -2 | -4 | -6 | -8 | -5 | -5 | -5 | -5 | -6 | -8 | -8 | -4 | -6 | -6 | -6 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -6 | -6 | -4 | -6 | -7 | -8 | -8 | -8 | -6 | -7 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -8 | -6 | -6 | -8 | -8 | -8 | -8 | -8 | -4 | -4 | -5 | -3 | -4 | -8 | -8 | -4 | -3 | -2 | -2 | -3 | -8 | -8 | -6 | -4 | -2 | -2 | -4 | -8 | -8 | -4 | -4 | -8 | -8 | -8 | -8 | -8 | -5 | -5 | -8 | -7 | -7 | -8 | -8 | -8 | -7 | -8 | -7 | -8 | -8 | -8 | -7 | -8 | -8 | -8 | -8 | -8 | -8 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 |  | 0 | -1 | -1 | 1 | -6 | -6 | -6 | 0 | 0 | 0 | -1 | -1 | -6 | -6 | -1 | -1 | -1 | -1 | -1 | -6 | -6 | 3 | 3 | 3 | 2 | 1 | 6 | 6 | 1 | 1 | 0 | 0 | -1 | 6 | 6 | -3 | -3 | -4 | -4 | -2 | 6 | 6 | -2 | -3 | -3 | -2 | -1 | 6 | 6 | -2 | -3 | -3 | -3 | -2 | 6 | 6 | -1 | -1 | -1 | -2 | 0 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | -2 | -2 | -2 | -2 | -2 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | -1 | -1 | -1 | -1 | -1 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 3 | 2 | 3 | 2 | 3 | 6 | 6 | 0 | 3 | 1 | 3 | 1 | 6 | 6 | 1 | 0 | 1 | 2 | 3 | 6 | 6 | 0 | 2 | 0 | 2 | 0 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 1 | 3 | 1 | 3 | 1 | 8 | 8 | 3 | 2 | 3 | 2 | 2 | 8 | 8 | 0 | 1 | 0 | 1 | 0 | 8 | 8 | 4 | 3 | 4 | 3 | 4 | 11 | 11 | 3 | 3 | 3 | 3 | 3 | 11 | 11 | -3 | -3 | -3 | -3 | -3 | 11 | 11 | 2 | 1 | 2 | 1 | 2 | 11 | 11 | 1 | 0 | 2 | 0 | 2 | 11 | 11 | 4 | 3 | 4 | 3 | 4 | 11 | 11 | 6 | 6 | 5 | 6 | 6 | 11 | 11 | 10 | 5 | 4 | 5 | 5 | 11 | 11 | 7 | 5 | 5 | 4 | 5 | 11 | 11 | 5 | 4 | 5 | 4 | 5 | 11 | 11 | 2 | 0 | 0 | 2 | 2 | 10 | 10 | 2 | 4 | 1 | 3 | 2 | 10 | 10 | 3 | 3 | 2 | 4 | 10 | 10 | 10 | 2 | 1 | 0 | 1 | 3 | 10 | 10 | 4 | 4 | 3 | 5 | 5 | 10 | 10 | 6 | 6 | 5 | 6 | 6 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 10 | 10 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 10 | 10 | 7 | 7 | 7 | 7 | 7 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 8 | 9 | 8 | 9 | 8 | 10 | 10 | 9 | 10 | 9 | 10 | 9 | 10 | 10 | 9 | 10 | 9 | 10 | 9 | 10 | 10
[481 empty] | 4.4 | [6 empty] | 4.6 | [6 empty] | 5.2 | [6 empty] | 4 | [6 empty] | 6.2 | [6 empty] | 5.6 | [6 empty] | 7.6 | [6 empty] | 7.4 | [6 empty] | 8 | [6 empty] | 14 | [6 empty] | 9.4 | [6 empty] | 10 | [6 empty] | 7.4 | [6 empty] | 5.2 | [6 empty] | 5.2 | [6 empty] | 5.8 | [6 empty] | 6.4 | [6 empty] | 8.8 | [6 empty] | 7.6 | [6 empty] | 5.6 | [6 empty] | 8.6 | [6 empty] | 5.8 | [6 empty] | 4.2 | [6 empty] | 4 | [6 empty] | 6 | [6 empty] | 5
ESTIMATES IN PROGRESS
BID WINDOW
[519 empty] | 1 | 1 | 1 | 1 | 1 | [23 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
[533 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
[548 empty] | 1 | 1 | 1 | 1 |  |  | 1
Tilton Fiber Project. | bar: 2025-02-16 W; 2025-03-09 T; 2026-05-31 M to 2026-05-31 F; 2026-06-07 M to 2026-06-07 F; 2026-06-14 M to 2026-06-14 F
CITY OF DICKINSON H2S ADDITIONS | bar: 2025-02-16 W; 2025-03-09 T; 2026-06-07 M to 2026-06-07 F; 2026-06-14 M to 2026-06-14 F; 2026-07-19 M to 2026-07-19 W
CITY OF DICKINSON PLC RETROFITS | bar: 2025-02-16 W; 2025-03-09 T; 2026-06-14 M to 2026-06-14 F; 2026-11-01 M to 2026-11-01 F; 2026-11-08 M to 2026-11-08 F; 2026-11-15 M to 2026-11-15 F; 2026-11-22 M to 2026-11-22 F; 2026-11-29 M to 2026-11-29 F
Future OneOK C&E Projects (follow up with customer to see if more will happen this year) | bar: 2025-02-16 W; 2025-03-09 T
KBS PROGRAMMING WORK | bar: 2025-02-16 W; 2025-03-09 T; 2026-07-12 M to 2026-07-12 F; 2026-07-19 M to 2026-07-19 F; 2026-08-02 M to 2026-08-02 F; 2026-08-09 M to 2026-08-09 F
[631 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
KBS PROGRAMMING WORK FLORIDA | bar: 2025-02-16 W; 2025-03-09 T
GEVO FUTURE 3 PHASE CNETRIFUGE DESIGN | bar: 2025-02-16 W; 2025-03-09 T
LITTLE KNIFE GAS PLANT HMI MOVES? | bar: 2025-02-16 W; 2025-03-09 T; 2026-07-05 M to 2026-07-05 F; 2026-07-12 M to 2026-07-12 F
GEVO DEBOTTLENECKING PANEL BUILD | bar: 2025-02-16 W; 2025-03-09 T; 2026-06-28 M to 2026-06-28 F; 2026-07-05 M to 2026-07-05 F; 2026-07-12 M to 2026-07-12 F
GEVO GRIND STRUCTURE | bar: 2025-02-16 W; 2025-03-09 T; 2026-07-19 W to 2026-07-19 F; 2026-07-26 M to 2026-07-26 F; 2026-08-02 M to 2026-08-02 F; 2026-08-09 M to 2026-08-09 F; 2026-08-16 M to 2026-08-16 F; 2026-08-23 M to 2026-08-23 F; 2026-08-30 M to 2026-08-30 F
POTENTIAL PROJECTS!!!! |  |  |  |  | ADD A YELLOW BAR ABOVE TO ADD THE ESTIMATES IN PROGRESS |  | 2024-09-22 T: 1; 2024-10-20 F: 1; 2024-11-10 M: 4; 2024-12-15 S: 4
[77 empty] | 1 | [17 empty] | 1 | [16 empty] | 4 | [40 empty] | 4 | [32 empty] | 4
[65 empty] | 1 | [27 empty] | 1
1
GEVO NEW CENTRIFUGE DESIGN / COORDINATION
GND Structure |  |  |  |  | ACTUAL WORKLOAD |  | 2026-04-12 M: #REF!; 2026-04-12 T: #REF!; 2026-04-12 W: #REF!; 2026-04-12 T: #REF!; 2026-04-12 F: #REF!; 2026-04-12 S: #REF!; 2026-04-12 S: #REF!; 2026-04-19 M: #REF!; 2026-04-19 T: #REF!; 2026-04-19 W: #REF!; 2026-04-19 T: #REF!; 2026-04-19 F: #REF!; 2026-04-19 S: #REF!; 2026-04-19 S: #REF!; 2026-04-26 M: #REF!; 2026-04-26 T: #REF!; 2026-04-26 W: #REF!; 2026-04-26 T: #REF!; 2026-04-26 F: #REF!; 2026-04-26 S: #REF!; 2026-04-26 S: #REF!; 2026-05-03 M: #REF!; 2026-05-03 T: #REF!; 2026-05-03 W: #REF!; 2026-05-03 T: #REF!; 2026-05-03 F: #REF!; 2026-05-03 S: #REF!; 2026-05-03 S: #REF!; 2026-05-10 M: #REF!; 2026-05-10 T: #REF!; 2026-05-10 W: #REF!; 2026-05-10 T: #REF!; 2026-05-10 F: #REF!; 2026-05-10 S: #REF!; 2026-05-10 S: #REF!; 2026-05-17 M: #REF!; 2026-05-17 T: #REF!; 2026-05-17 W: #REF!; 2026-05-17 T: #REF!; 2026-05-17 F: #REF!; 2026-05-17 S: #REF!; 2026-05-17 S: #REF!; 2026-05-24 M: #REF!; 2026-05-24 T: #REF!; 2026-05-24 W: #REF!; 2026-05-24 T: #REF!; 2026-05-24 F: #REF!; 2026-05-24 S: #REF!; 2026-05-24 S: #REF!; 2026-05-31 M: #REF!; 2026-05-31 T: #REF!; 2026-05-31 W: #REF!; 2026-05-31 T: #REF!; 2026-05-31 F: #REF!; 2026-05-31 S: #REF!; 2026-05-31 S: #REF!; 2026-06-07 M: #REF!; 2026-06-07 T: #REF!; 2026-06-07 W: #REF!; 2026-06-07 T: #REF!; 2026-06-07 F: #REF!; 2026-06-07 S: #REF!; 2026-06-07 S: #REF!; 2026-06-14 M: #REF!; 2026-06-14 T: #REF!; 2026-06-14 W: #REF!; 2026-06-14 T: #REF!; 2026-06-14 F: #REF!; 2026-06-14 S: #REF!; 2026-06-14 S: #REF!; 2026-06-21 M: 8; 2026-06-21 T: 10; 2026-06-21 W: 10; 2026-06-21 T: 8; 2026-06-21 F: 8; 2026-06-21 S: 0; 2026-06-21 S: 0; 2026-06-28 M: 8; 2026-06-28 T: 6; 2026-06-28 W: 9; 2026-06-28 T: 7; 2026-06-28 F: 8; 2026-06-28 S: 0; 2026-06-28 S: 0; 2026-07-05 M: 7; 2026-07-05 T: 7; 2026-07-05 W: 8; 2026-07-05 T: 6; 2026-07-05 F: 0; 2026-07-05 S: 0; 2026-07-05 S: 0; 2026-07-12 M: 8; 2026-07-12 T: 9; 2026-07-12 W: 10; 2026-07-12 T: 9; 2026-07-12 F: 7; 2026-07-12 S: 0; 2026-07-12 S: 0; 2026-07-19 M: 6; 2026-07-19 T: 6; 2026-07-19 W: 7; 2026-07-19 T: 5; 2026-07-19 F: 5; 2026-07-19 S: 0; 2026-07-19 S: 0; 2026-07-26 M: 4; 2026-07-26 T: 4; 2026-07-26 W: 5; 2026-07-26 T: 4; 2026-07-26 F: 4; 2026-07-26 S: 0; 2026-07-26 S: 0; 2026-08-02 M: 4; 2026-08-02 T: 4; 2026-08-02 W: 4; 2026-08-02 T: 4; 2026-08-02 F: 4; 2026-08-02 S: 0; 2026-08-02 S: 0; 2026-08-09 M: 6; 2026-08-09 T: 6; 2026-08-09 W: 6; 2026-08-09 T: 6; 2026-08-09 F: 6; 2026-08-09 S: 0; 2026-08-09 S: 0; 2026-08-16 M: 5; 2026-08-16 T: 5; 2026-08-16 W: 5; 2026-08-16 T: 5; 2026-08-16 F: 5; 2026-08-16 S: 0; 2026-08-16 S: 0; 2026-08-23 M: 4; 2026-08-23 T: 4; 2026-08-23 W: 4; 2026-08-23 T: 4; 2026-08-23 F: 4; 2026-08-23 S: 0; 2026-08-23 S: 0; 2026-08-30 M: 4; 2026-08-30 T: 4; 2026-08-30 W: 4; 2026-08-30 T: 4; 2026-08-30 F: 4; 2026-08-30 S: 0; 2026-08-30 S: 0; 2026-09-06 M: 3; 2026-09-06 T: 3; 2026-09-06 W: 3; 2026-09-06 T: 3; 2026-09-06 F: 3; 2026-09-06 S: 0; 2026-09-06 S: 0; 2026-09-13 M: 2; 2026-09-13 T: 2; 2026-09-13 W: 2; 2026-09-13 T: 2; 2026-09-13 F: 2; 2026-09-13 S: 0; 2026-09-13 S: 0; 2026-09-20 M: 2; 2026-09-20 T: 2; 2026-09-20 W: 2; 2026-09-20 T: 2; 2026-09-20 F: 2; 2026-09-20 S: 0; 2026-09-20 S: 0; 2026-09-27 M: 2; 2026-09-27 T: 2; 2026-09-27 W: 2; 2026-09-27 T: 2; 2026-09-27 F: 2; 2026-09-27 S: 0; 2026-09-27 S: 0; 2026-10-04 M: 2; 2026-10-04 T: 2; 2026-10-04 W: 2; 2026-10-04 T: 2; 2026-10-04 F: 2; 2026-10-04 S: 0; 2026-10-04 S: 0; 2026-10-11 M: 2; 2026-10-11 T: 1; 2026-10-11 W: 2; 2026-10-11 T: 1; 2026-10-11 F: 2; 2026-10-11 S: 0; 2026-10-11 S: 0; 2026-10-18 M: 2; 2026-10-18 T: 1; 2026-10-18 W: 2; 2026-10-18 T: 1; 2026-10-18 F: 2; 2026-10-18 S: 0; 2026-10-18 S: 0; 2026-10-25 M: 2; 2026-10-25 T: 1; 2026-10-25 W: 2; 2026-10-25 T: 1; 2026-10-25 F: 2; 2026-10-25 S: 0; 2026-10-25 S: 0; 2026-11-01 M: 2; 2026-11-01 T: 1; 2026-11-01 W: 2; 2026-11-01 T: 1; 2026-11-01 F: 2; 2026-11-01 S: 0; 2026-11-01 S: 0; 2026-11-08 M: 2; 2026-11-08 T: 1; 2026-11-08 W: 2; 2026-11-08 T: 1; 2026-11-08 F: 2; 2026-11-08 S: 0; 2026-11-08 S: 0; 2026-11-15 M: 2; 2026-11-15 T: 1; 2026-11-15 W: 2; 2026-11-15 T: 1; 2026-11-15 F: 2; 2026-11-15 S: 0; 2026-11-15 S: 0; 2026-11-22 M: 2; 2026-11-22 T: 1; 2026-11-22 W: 2; 2026-11-22 T: 1; 2026-11-22 F: 2; 2026-11-22 S: 0; 2026-11-22 S: 0; 2026-11-29 M: 2; 2026-11-29 T: 1; 2026-11-29 W: 2; 2026-11-29 T: 1; 2026-11-29 F: 2; 2026-11-29 S: 0; 2026-11-29 S: 0; 2026-12-07 M: 2; 2026-12-07 T: 1; 2026-12-07 W: 2; 2026-12-07 T: 1; 2026-12-07 F: 2; 2026-12-07 S: 0; 2026-12-07 S: 0; 2026-12-13 M: 2; 2026-12-13 T: 1; 2026-12-13 W: 2; 2026-12-13 T: 1; 2026-12-13 F: 2; 2026-12-13 S: 0; 2026-12-13 S: 0; 2026-12-20 M: 2; 2026-12-20 T: 1; 2026-12-20 W: 2; 2026-12-20 T: 1; 2026-12-20 F: 2; 2026-12-20 S: 0; 2026-12-20 S: 0; 2026-12-27 M: 1; 2026-12-27 T: 0; 2026-12-27 W: 1; 2026-12-27 T: 0; 2026-12-27 F: 1; 2026-12-27 S: 0; 2026-12-27 S: 0; 2027-01-04 M: 1; 2027-01-04 T: 0; 2027-01-04 W: 1; 2027-01-04 T: 0; 2027-01-04 F: 1; 2027-01-04 S: 0; 2027-01-04 S: 0
Debottling System |  |  |  |  | POETENTIAL WORK LOAD |  | 2025-10-05 M: #REF!; 2025-10-05 T: #REF!; 2025-10-05 W: #REF!; 2025-10-05 T: #REF!; 2025-10-05 F: #REF!; 2025-10-05 S: #REF!; 2025-10-05 S: #REF!; 2025-10-12 M: #REF!; 2025-10-12 T: #REF!; 2025-10-12 W: #REF!; 2025-10-12 T: #REF!; 2025-10-12 F: #REF!; 2025-10-12 S: #REF!; 2025-10-12 S: #REF!; 2025-10-19 M: #REF!; 2025-10-19 T: #REF!; 2025-10-19 W: #REF!; 2025-10-19 T: #REF!; 2025-10-19 F: #REF!; 2025-10-19 S: #REF!; 2025-10-19 S: #REF!; 2025-10-26 M: #REF!; 2025-10-26 T: #REF!; 2025-10-26 W: #REF!; 2025-10-26 T: #REF!; 2025-10-26 F: #REF!; 2025-10-26 S: #REF!; 2025-10-26 S: #REF!; 2025-11-02 M: #REF!; 2025-11-02 T: #REF!; 2025-11-02 W: #REF!; 2025-11-02 T: #REF!; 2025-11-02 F: #REF!; 2025-11-02 S: #REF!; 2025-11-02 S: #REF!; 2025-11-09 M: #REF!; 2025-11-09 T: #REF!; 2025-11-09 W: #REF!; 2025-11-09 T: #REF!; 2025-11-09 F: #REF!; 2025-11-09 S: #REF!; 2025-11-09 S: #REF!; 2025-11-16 M: #REF!; 2025-11-16 T: #REF!; 2025-11-16 W: #REF!; 2025-11-16 T: #REF!; 2025-11-16 F: #REF!; 2025-11-16 S: #REF!; 2025-11-16 S: #REF!; 2025-11-23 M: #REF!; 2025-11-23 T: #REF!; 2025-11-23 W: #REF!; 2025-11-23 T: #REF!; 2025-11-23 F: #REF!; 2025-11-23 S: #REF!; 2025-11-23 S: #REF!; 2025-11-30 M: #REF!; 2025-11-30 T: #REF!; 2025-11-30 W: #REF!; 2025-11-30 T: #REF!; 2025-11-30 F: #REF!; 2025-11-30 S: #REF!; 2025-11-30 S: #REF!; 2025-12-07 M: #REF!; 2025-12-07 T: #REF!; 2025-12-07 W: #REF!; 2025-12-07 T: #REF!; 2025-12-07 F: #REF!; 2025-12-07 S: #REF!; 2025-12-07 S: #REF!; 2025-12-14 M: #REF!; 2025-12-14 T: #REF!; 2025-12-14 W: #REF!; 2025-12-14 T: #REF!; 2025-12-14 F: #REF!; 2025-12-14 S: #REF!; 2025-12-14 S: #REF!; 2025-12-21 M: #REF!; 2025-12-21 T: #REF!; 2025-12-21 W: #REF!; 2025-12-21 T: #REF!; 2025-12-21 F: #REF!; 2025-12-21 S: #REF!; 2025-12-21 S: #REF!; 2025-12-28 M: #REF!; 2025-12-28 T: #REF!; 2025-12-28 W: #REF!; 2025-12-28 T: #REF!; 2025-12-28 F: #REF!; 2025-12-28 S: #REF!; 2025-12-28 S: #REF!; 2026-01-04 M: #REF!; 2026-01-04 T: #REF!; 2026-01-04 W: #REF!; 2026-01-04 T: #REF!; 2026-01-04 F: #REF!; 2026-01-04 S: #REF!; 2026-01-04 S: #REF!; 2026-01-11 M: #REF!; 2026-01-11 T: #REF!; 2026-01-11 W: #REF!; 2026-01-11 T: #REF!; 2026-01-11 F: #REF!; 2026-01-11 S: #REF!; 2026-01-11 S: #REF!; 2026-01-18 M: #REF!; 2026-01-18 T: #REF!; 2026-01-18 W: #REF!; 2026-01-18 T: #REF!; 2026-01-18 F: #REF!; 2026-01-18 S: #REF!; 2026-01-18 S: #REF!; 2026-01-25 M: #REF!; 2026-01-25 T: #REF!; 2026-01-25 W: #REF!; 2026-01-25 T: #REF!; 2026-01-25 F: #REF!; 2026-01-25 S: #REF!; 2026-01-25 S: #REF!; 2026-02-01 M: #REF!; 2026-02-01 T: #REF!; 2026-02-01 W: #REF!; 2026-02-01 T: #REF!; 2026-02-01 F: #REF!; 2026-02-01 S: #REF!; 2026-02-01 S: #REF!; 2026-02-08 M: #REF!; 2026-02-08 T: #REF!; 2026-02-08 W: #REF!; 2026-02-08 T: #REF!; 2026-02-08 F: #REF!; 2026-02-08 S: #REF!; 2026-02-08 S: #REF!; 2026-02-15 M: #REF!; 2026-02-15 T: #REF!; 2026-02-15 W: #REF!; 2026-02-15 T: #REF!; 2026-02-15 F: #REF!; 2026-02-15 S: #REF!; 2026-02-15 S: #REF!; 2026-02-22 M: #REF!; 2026-02-22 T: #REF!; 2026-02-22 W: #REF!; 2026-02-22 T: #REF!; 2026-02-22 F: #REF!; 2026-02-22 S: #REF!; 2026-02-22 S: #REF!; 2026-03-01 M: #REF!; 2026-03-01 T: #REF!; 2026-03-01 W: #REF!; 2026-03-01 T: #REF!; 2026-03-01 F: #REF!; 2026-03-01 S: #REF!; 2026-03-01 S: #REF!; 2026-03-08 M: #REF!; 2026-03-08 T: #REF!; 2026-03-08 W: #REF!; 2026-03-08 T: #REF!; 2026-03-08 F: #REF!; 2026-03-08 S: #REF!; 2026-03-08 S: #REF!; 2026-03-15 M: #REF!; 2026-03-15 T: #REF!; 2026-03-15 W: #REF!; 2026-03-15 T: #REF!; 2026-03-15 F: #REF!; 2026-03-15 S: #REF!; 2026-03-15 S: #REF!; 2026-03-22 M: #REF!; 2026-03-22 T: #REF!; 2026-03-22 W: #REF!; 2026-03-22 T: #REF!; 2026-03-22 F: #REF!; 2026-03-22 S: #REF!; 2026-03-22 S: #REF!; 2026-03-29 M: #REF!; 2026-03-29 T: #REF!; 2026-03-29 W: #REF!; 2026-03-29 T: #REF!; 2026-03-29 F: #REF!; 2026-03-29 S: #REF!; 2026-03-29 S: #REF!; 2026-04-05 M: #REF!; 2026-04-05 T: #REF!; 2026-04-05 W: #REF!; 2026-04-05 T: #REF!; 2026-04-05 F: #REF!; 2026-04-05 S: #REF!; 2026-04-05 S: #REF!; 2026-04-12 M: #REF!; 2026-04-12 T: #REF!; 2026-04-12 W: #REF!; 2026-04-12 T: #REF!; 2026-04-12 F: #REF!; 2026-04-12 S: #REF!; 2026-04-12 S: #REF!; 2026-04-19 M: #REF!; 2026-04-19 T: #REF!; 2026-04-19 W: #REF!; 2026-04-19 T: #REF!; 2026-04-19 F: #REF!; 2026-04-19 S: #REF!; 2026-04-19 S: #REF!; 2026-04-26 M: #REF!; 2026-04-26 T: #REF!; 2026-04-26 W: #REF!; 2026-04-26 T: #REF!; 2026-04-26 F: #REF!; 2026-04-26 S: #REF!; 2026-04-26 S: #REF!; 2026-05-03 M: #REF!; 2026-05-03 T: #REF!; 2026-05-03 W: #REF!; 2026-05-03 T: #REF!; 2026-05-03 F: #REF!; 2026-05-03 S: #REF!; 2026-05-03 S: #REF!; 2026-05-10 M: #REF!; 2026-05-10 T: #REF!; 2026-05-10 W: #REF!; 2026-05-10 T: #REF!; 2026-05-10 F: #REF!; 2026-05-10 S: #REF!; 2026-05-10 S: #REF!; 2026-05-17 M: #REF!; 2026-05-17 T: #REF!; 2026-05-17 W: #REF!; 2026-05-17 T: #REF!; 2026-05-17 F: #REF!; 2026-05-17 S: #REF!; 2026-05-17 S: #REF!; 2026-05-24 M: #REF!; 2026-05-24 T: #REF!; 2026-05-24 W: #REF!; 2026-05-24 T: #REF!; 2026-05-24 F: #REF!; 2026-05-24 S: #REF!; 2026-05-24 S: #REF!; 2026-05-31 M: #REF!; 2026-05-31 T: #REF!; 2026-05-31 W: #REF!; 2026-05-31 T: #REF!; 2026-05-31 F: #REF!; 2026-05-31 S: #REF!; 2026-05-31 S: #REF!; 2026-06-07 M: #REF!; 2026-06-07 T: #REF!; 2026-06-07 W: #REF!; 2026-06-07 T: #REF!; 2026-06-07 F: #REF!; 2026-06-07 S: #REF!; 2026-06-07 S: #REF!; 2026-06-14 M: #REF!; 2026-06-14 T: #REF!; 2026-06-14 W: #REF!; 2026-06-14 T: #REF!; 2026-06-14 F: #REF!; 2026-06-14 S: #REF!; 2026-06-14 S: #REF!; 2026-06-21 M: 0; 2026-06-21 T: 0; 2026-06-21 W: 0; 2026-06-21 T: 0; 2026-06-21 F: 0; 2026-06-21 S: 0; 2026-06-21 S: 0; 2026-06-28 M: 1; 2026-06-28 T: 1; 2026-06-28 W: 1; 2026-06-28 T: 1; 2026-06-28 F: 1; 2026-06-28 S: 0; 2026-06-28 S: 0; 2026-07-05 M: 2; 2026-07-05 T: 2; 2026-07-05 W: 2; 2026-07-05 T: 2; 2026-07-05 F: 2; 2026-07-05 S: 0; 2026-07-05 S: 0; 2026-07-12 M: 3; 2026-07-12 T: 3; 2026-07-12 W: 3; 2026-07-12 T: 3; 2026-07-12 F: 3; 2026-07-12 S: 0; 2026-07-12 S: 0; 2026-07-19 M: 2; 2026-07-19 T: 2; 2026-07-19 W: 3; 2026-07-19 T: 2; 2026-07-19 F: 2; 2026-07-19 S: 0; 2026-07-19 S: 0; 2026-07-26 M: 2; 2026-07-26 T: 2; 2026-07-26 W: 2; 2026-07-26 T: 2; 2026-07-26 F: 2; 2026-07-26 S: 0; 2026-07-26 S: 0; 2026-08-02 M: 2; 2026-08-02 T: 3; 2026-08-02 W: 3; 2026-08-02 T: 3; 2026-08-02 F: 3; 2026-08-02 S: 0; 2026-08-02 S: 0; 2026-08-09 M: 3; 2026-08-09 T: 3; 2026-08-09 W: 3; 2026-08-09 T: 3; 2026-08-09 F: 3; 2026-08-09 S: 0; 2026-08-09 S: 0; 2026-08-16 M: 2; 2026-08-16 T: 2; 2026-08-16 W: 2; 2026-08-16 T: 2; 2026-08-16 F: 2; 2026-08-16 S: 0; 2026-08-16 S: 0; 2026-08-23 M: 2; 2026-08-23 T: 2; 2026-08-23 W: 2; 2026-08-23 T: 2; 2026-08-23 F: 2; 2026-08-23 S: 0; 2026-08-23 S: 0; 2026-08-30 M: 1; 2026-08-30 T: 1; 2026-08-30 W: 1; 2026-08-30 T: 1; 2026-08-30 F: 1; 2026-08-30 S: 0; 2026-08-30 S: 0; 2026-09-06 M: 0; 2026-09-06 T: 0; 2026-09-06 W: 0; 2026-09-06 T: 0; 2026-09-06 F: 0; 2026-09-06 S: 0; 2026-09-06 S: 0; 2026-09-13 M: 0; 2026-09-13 T: 0; 2026-09-13 W: 0; 2026-09-13 T: 0; 2026-09-13 F: 0; 2026-09-13 S: 0; 2026-09-13 S: 0; 2026-09-20 M: 0; 2026-09-20 T: 0; 2026-09-20 W: 0; 2026-09-20 T: 0; 2026-09-20 F: 0; 2026-09-20 S: 0; 2026-09-20 S: 0; 2026-09-27 M: 0; 2026-09-27 T: 0; 2026-09-27 W: 0; 2026-09-27 T: 0; 2026-09-27 F: 0; 2026-09-27 S: 0; 2026-09-27 S: 0; 2026-10-04 M: 0; 2026-10-04 T: 0; 2026-10-04 W: 0; 2026-10-04 T: 0; 2026-10-04 F: 0; 2026-10-04 S: 0; 2026-10-04 S: 0; 2026-10-11 M: 0; 2026-10-11 T: 0; 2026-10-11 W: 0; 2026-10-11 T: 0; 2026-10-11 F: 0; 2026-10-11 S: 0; 2026-10-11 S: 0; 2026-10-18 M: 0; 2026-10-18 T: 0; 2026-10-18 W: 0; 2026-10-18 T: 0; 2026-10-18 F: 0; 2026-10-18 S: 0; 2026-10-18 S: 0; 2026-10-25 M: 0; 2026-10-25 T: 0; 2026-10-25 W: 0; 2026-10-25 T: 0; 2026-10-25 F: 0; 2026-10-25 S: 0; 2026-10-25 S: 0; 2026-11-01 M: 1; 2026-11-01 T: 1; 2026-11-01 W: 1; 2026-11-01 T: 1; 2026-11-01 F: 1; 2026-11-01 S: 0; 2026-11-01 S: 0; 2026-11-08 M: 1; 2026-11-08 T: 1; 2026-11-08 W: 1; 2026-11-08 T: 1; 2026-11-08 F: 1; 2026-11-08 S: 0; 2026-11-08 S: 0; 2026-11-15 M: 1; 2026-11-15 T: 1; 2026-11-15 W: 1; 2026-11-15 T: 1; 2026-11-15 F: 1; 2026-11-15 S: 0; 2026-11-15 S: 0; 2026-11-22 M: 1; 2026-11-22 T: 1; 2026-11-22 W: 1; 2026-11-22 T: 1; 2026-11-22 F: 1; 2026-11-22 S: 0; 2026-11-22 S: 0; 2026-11-29 M: 1; 2026-11-29 T: 1; 2026-11-29 W: 1; 2026-11-29 T: 1; 2026-11-29 F: 1; 2026-11-29 S: 0; 2026-11-29 S: 0; 2026-12-07 M: 0; 2026-12-07 T: 0; 2026-12-07 W: 0; 2026-12-07 T: 0; 2026-12-07 F: 0; 2026-12-07 S: 0; 2026-12-07 S: 0; 2026-12-13 M: 0; 2026-12-13 T: 0; 2026-12-13 W: 0; 2026-12-13 T: 0; 2026-12-13 F: 0; 2026-12-13 S: 0; 2026-12-13 S: 0; 2026-12-20 M: 0; 2026-12-20 T: 0; 2026-12-20 W: 0; 2026-12-20 T: 0; 2026-12-20 F: 0; 2026-12-20 S: 0; 2026-12-20 S: 0; 2026-12-27 M: 0; 2026-12-27 T: 0; 2026-12-27 W: 0; 2026-12-27 T: 0; 2026-12-27 F: 0; 2026-12-27 S: 0; 2026-12-27 S: 0; 2027-01-04 M: 0; 2027-01-04 T: 0; 2027-01-04 W: 0; 2027-01-04 T: 0; 2027-01-04 F: 0; 2027-01-04 S: 0; 2027-01-04 S: 0
[5 empty] | POTENTIAL COMBINED WORKLOAD |  | 2026-04-12 M: #REF!; 2026-04-12 T: #REF!; 2026-04-12 W: #REF!; 2026-04-12 T: #REF!; 2026-04-12 F: #REF!; 2026-04-12 S: #REF!; 2026-04-12 S: #REF!; 2026-04-19 M: #REF!; 2026-04-19 T: #REF!; 2026-04-19 W: #REF!; 2026-04-19 T: #REF!; 2026-04-19 F: #REF!; 2026-04-19 S: #REF!; 2026-04-19 S: #REF!; 2026-04-26 M: #REF!; 2026-04-26 T: #REF!; 2026-04-26 W: #REF!; 2026-04-26 T: #REF!; 2026-04-26 F: #REF!; 2026-04-26 S: #REF!; 2026-04-26 S: #REF!; 2026-05-03 M: #REF!; 2026-05-03 T: #REF!; 2026-05-03 W: #REF!; 2026-05-03 T: #REF!; 2026-05-03 F: #REF!; 2026-05-03 S: #REF!; 2026-05-03 S: #REF!; 2026-05-10 M: #REF!; 2026-05-10 T: #REF!; 2026-05-10 W: #REF!; 2026-05-10 T: #REF!; 2026-05-10 F: #REF!; 2026-05-10 S: #REF!; 2026-05-10 S: #REF!; 2026-05-17 M: #REF!; 2026-05-17 T: #REF!; 2026-05-17 W: #REF!; 2026-05-17 T: #REF!; 2026-05-17 F: #REF!; 2026-05-17 S: #REF!; 2026-05-17 S: #REF!; 2026-05-24 M: #REF!; 2026-05-24 T: #REF!; 2026-05-24 W: #REF!; 2026-05-24 T: #REF!; 2026-05-24 F: #REF!; 2026-05-24 S: #REF!; 2026-05-24 S: #REF!; 2026-05-31 M: #REF!; 2026-05-31 T: #REF!; 2026-05-31 W: #REF!; 2026-05-31 T: #REF!; 2026-05-31 F: #REF!; 2026-05-31 S: #REF!; 2026-05-31 S: #REF!; 2026-06-07 M: #REF!; 2026-06-07 T: #REF!; 2026-06-07 W: #REF!; 2026-06-07 T: #REF!; 2026-06-07 F: #REF!; 2026-06-07 S: #REF!; 2026-06-07 S: #REF!; 2026-06-14 M: #REF!; 2026-06-14 T: #REF!; 2026-06-14 W: #REF!; 2026-06-14 T: #REF!; 2026-06-14 F: #REF!; 2026-06-14 S: #REF!; 2026-06-14 S: #REF!; 2026-06-21 M: 8; 2026-06-21 T: 10; 2026-06-21 W: 10; 2026-06-21 T: 8; 2026-06-21 F: 8; 2026-06-21 S: 0; 2026-06-21 S: 0; 2026-06-28 M: 9; 2026-06-28 T: 7; 2026-06-28 W: 10; 2026-06-28 T: 8; 2026-06-28 F: 9; 2026-06-28 S: 0; 2026-06-28 S: 0; 2026-07-05 M: 9; 2026-07-05 T: 9; 2026-07-05 W: 10; 2026-07-05 T: 8; 2026-07-05 F: 2; 2026-07-05 S: 0; 2026-07-05 S: 0; 2026-07-12 M: 11; 2026-07-12 T: 12; 2026-07-12 W: 13; 2026-07-12 T: 12; 2026-07-12 F: 10; 2026-07-12 S: 0; 2026-07-12 S: 0; 2026-07-19 M: 8; 2026-07-19 T: 8; 2026-07-19 W: 10; 2026-07-19 T: 7; 2026-07-19 F: 7; 2026-07-19 S: 0; 2026-07-19 S: 0; 2026-07-26 M: 6; 2026-07-26 T: 6; 2026-07-26 W: 7; 2026-07-26 T: 6; 2026-07-26 F: 6; 2026-07-26 S: 0; 2026-07-26 S: 0; 2026-08-02 M: 6; 2026-08-02 T: 7; 2026-08-02 W: 7; 2026-08-02 T: 7; 2026-08-02 F: 7; 2026-08-02 S: 0; 2026-08-02 S: 0; 2026-08-09 M: 9; 2026-08-09 T: 9; 2026-08-09 W: 9; 2026-08-09 T: 9; 2026-08-09 F: 9; 2026-08-09 S: 0; 2026-08-09 S: 0; 2026-08-16 M: 7; 2026-08-16 T: 7; 2026-08-16 W: 7; 2026-08-16 T: 7; 2026-08-16 F: 7; 2026-08-16 S: 0; 2026-08-16 S: 0; 2026-08-23 M: 6; 2026-08-23 T: 6; 2026-08-23 W: 6; 2026-08-23 T: 6; 2026-08-23 F: 6; 2026-08-23 S: 0; 2026-08-23 S: 0; 2026-08-30 M: 5; 2026-08-30 T: 5; 2026-08-30 W: 5; 2026-08-30 T: 5; 2026-08-30 F: 5; 2026-08-30 S: 0; 2026-08-30 S: 0; 2026-09-06 M: 3; 2026-09-06 T: 3; 2026-09-06 W: 3; 2026-09-06 T: 3; 2026-09-06 F: 3; 2026-09-06 S: 0; 2026-09-06 S: 0; 2026-09-13 M: 2; 2026-09-13 T: 2; 2026-09-13 W: 2; 2026-09-13 T: 2; 2026-09-13 F: 2; 2026-09-13 S: 0; 2026-09-13 S: 0; 2026-09-20 M: 2; 2026-09-20 T: 2; 2026-09-20 W: 2; 2026-09-20 T: 2; 2026-09-20 F: 2; 2026-09-20 S: 0; 2026-09-20 S: 0; 2026-09-27 M: 2; 2026-09-27 T: 2; 2026-09-27 W: 2; 2026-09-27 T: 2; 2026-09-27 F: 2; 2026-09-27 S: 0; 2026-09-27 S: 0; 2026-10-04 M: 2; 2026-10-04 T: 2; 2026-10-04 W: 2; 2026-10-04 T: 2; 2026-10-04 F: 2; 2026-10-04 S: 0; 2026-10-04 S: 0; 2026-10-11 M: 2; 2026-10-11 T: 1; 2026-10-11 W: 2; 2026-10-11 T: 1; 2026-10-11 F: 2; 2026-10-11 S: 0; 2026-10-11 S: 0; 2026-10-18 M: 2; 2026-10-18 T: 1; 2026-10-18 W: 2; 2026-10-18 T: 1; 2026-10-18 F: 2; 2026-10-18 S: 0; 2026-10-18 S: 0; 2026-10-25 M: 2; 2026-10-25 T: 1; 2026-10-25 W: 2; 2026-10-25 T: 1; 2026-10-25 F: 2; 2026-10-25 S: 0; 2026-10-25 S: 0; 2026-11-01 M: 3; 2026-11-01 T: 2; 2026-11-01 W: 3; 2026-11-01 T: 2; 2026-11-01 F: 3; 2026-11-01 S: 0; 2026-11-01 S: 0; 2026-11-08 M: 3; 2026-11-08 T: 2; 2026-11-08 W: 3; 2026-11-08 T: 2; 2026-11-08 F: 3; 2026-11-08 S: 0; 2026-11-08 S: 0; 2026-11-15 M: 3; 2026-11-15 T: 2; 2026-11-15 W: 3; 2026-11-15 T: 2; 2026-11-15 F: 3; 2026-11-15 S: 0; 2026-11-15 S: 0; 2026-11-22 M: 3; 2026-11-22 T: 2; 2026-11-22 W: 3; 2026-11-22 T: 2; 2026-11-22 F: 3; 2026-11-22 S: 0; 2026-11-22 S: 0; 2026-11-29 M: 3; 2026-11-29 T: 2; 2026-11-29 W: 3; 2026-11-29 T: 2; 2026-11-29 F: 3; 2026-11-29 S: 0; 2026-11-29 S: 0; 2026-12-07 M: 2; 2026-12-07 T: 1; 2026-12-07 W: 2; 2026-12-07 T: 1; 2026-12-07 F: 2; 2026-12-07 S: 0; 2026-12-07 S: 0; 2026-12-13 M: 2; 2026-12-13 T: 1; 2026-12-13 W: 2; 2026-12-13 T: 1; 2026-12-13 F: 2; 2026-12-13 S: 0; 2026-12-13 S: 0; 2026-12-20 M: 2; 2026-12-20 T: 1; 2026-12-20 W: 2; 2026-12-20 T: 1; 2026-12-20 F: 2; 2026-12-20 S: 0; 2026-12-20 S: 0; 2026-12-27 M: 1; 2026-12-27 T: 0; 2026-12-27 W: 1; 2026-12-27 T: 0; 2026-12-27 F: 1; 2026-12-27 S: 0; 2026-12-27 S: 0; 2027-01-04 M: 1; 2027-01-04 T: 0; 2027-01-04 W: 1; 2027-01-04 T: 0; 2027-01-04 F: 1; 2027-01-04 S: 0; 2027-01-04 S: 0
KBS PROGRAMMING WORK
[10 empty] | ENETK | [17 empty] | YES | [17 empty] | SHOP / OFFICE | [17 empty] | RESOURCE SUMMARY
|  |  |  | 6129 |  |  | 2024-07-28 T: CUSTOMER; 2024-08-04 T: EMPLOYEE; 2024-08-11 F: HAS TRUCK; 2024-08-18 M: CUSTOMER; 2024-08-25 M: EMPLOYEE; 2024-09-01 T: HAS TRUCK; 2024-09-01 F: CUSTOMER; 2024-09-08 F: EMPLOYEE; 2024-09-15 S: HAS TRUCK; 2024-09-22 T: ENTITY; 2024-09-29 T: COUNT
[17 empty] | KYLE MERRILL | [7 empty] | X | [9 empty] | JOSH CASAVANT (JW) | [7 empty] | X | [9 empty] | MATHEW ROTHSTEIN | [7 empty] | X |  |  | ENETK | [8 empty] | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 16
[17 empty] | SETH PETERSON | [7 empty] | X | [9 empty] | ELDON PRIVRATSKY (JW) | [7 empty] | X | [9 empty] | TYE PAUL | [10 empty] | Field Apprentices | [8 empty] | 12 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 15
[17 empty] | LOREN MCCRAY | [7 empty] | X | [9 empty] | JOHN HELMUTH (JW) | [7 empty] | X | [9 empty] | CHAD YSTAAS | [7 empty] | X |  |  | Field Journeyman | [8 empty] | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 14
[17 empty] | EARL WILSON | [17 empty] | AARON BURCKHARD (JW) | [7 empty] | X | [9 empty] | JERRY KARSKY | [7 empty] | X |  |  | Admin Journeyman | [8 empty] | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 13
[64 empty] | Total Journeyman | [8 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
[17 empty] | MATT HUBER | [7 empty] | X | [9 empty] | DOUG SUPRY (JW) | [7 empty] | X | [9 empty] | KRISTINA LEFORT | [10 empty] | Shop | [8 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
DEREK LUSE
[35 empty] | TANNER JARRETT (APP 2) | [7 empty] | X | [20 empty] | Total Field Staff | [8 empty] | 26
[17 empty] | AUSTIN JANGULA | [7 empty] | X | [9 empty] | ELI WILLIAMS (APP 3) | [28 empty] | Total With Shop | [8 empty] | 28
[17 empty] | ANDREW FICEK | [17 empty] | NATHAN SNELL (APP 2)
GABE GRANADA (APP 3)
[35 empty] | BRETT WENDEL (APP 1) | [28 empty] | Pending New Hires
Apprentice
[10 empty] | SUMMER INTERNS | [24 empty] | JESSSE BENHAM (APP4) | [28 empty] | Journeyman
[35 empty] | LUIS GUIZAR (APP 3) | [7 empty] | X | [20 empty] | I&E
[35 empty] | TANNER THORSTAD (APP 2) | [7 empty] | X
[35 empty] | AUSTIN SOUKUP (APP 1) | [28 empty] | Positions to Fill
[64 empty] | Apprentice | [8 empty] | 4
[35 empty] | TYSON ROBINSON (APP 2) | [7 empty] | X | [20 empty] | Journeyman | [8 empty] | 2
[35 empty] | ETHAN SMITH (APP 4) | [7 empty] | X | [20 empty] | I&E
ETHAN VANCE (APP 1 )
New Hires
Conner Hoenke
Jeremy Arrant
Hank Carter
Payton Hauge
Fox Weiler 4th year
Master Electricain
Journeyman Electrician
4th
3rd
2nd
1st
GM
Project Manager
Superintendent
Project Foreman
Lead Electrician
Journeyman